## Risk Register
Risk ID | Risk Category | Description | Likelihood | Impact | Risk Score | Response Strategy | Mitigation Plan | Risk Owner | Status | Review Date | Date Identified | Residual Risk Score | Control Effectiveness | Risk Trend | Next Review Date
1 | Patient Safety | Potential for patient data breach | High | High | 9 | Treat | Implement advanced encryption and access controls | CRO | Open | 2025-06-01 | 2025-01-01 | 4 | Moderate | Stable | 2025-12-01
2 | Compliance | Non-compliance with HIPAA regulations | Medium | High | 6 | Avoid | Regular compliance audits and staff training | Compliance Officer | Open | 2025-07-15 | 2025-02-15 | 3 | High | Decreasing | 2026-01-15
3 | Clinical Operations | Disruption in clinical operations due to equipment failure | Low | Medium | 3 | Accept | Preventive maintenance and regular equipment checks | COO | Closed | 2025-08-20 | 2025-03-20 | 1 | High | Stable | 2026-02-20
4 | IT Systems | IT system downtime affecting patient care | High | High | 9 | Transfer | Implement redundant systems and regular backups | CIO | Open | 2025-09-10 | 2025-04-10 | 5 | Low | Increasing | 2026-03-10
5 | Vendor Management | Vendor fails to deliver critical supplies | Medium | Low | 2 | Treat | Establish alternative suppliers and contingency plans | Procurement Manager | Closed | 2025-10-05 | 2025-05-05 | 1 | Moderate | Decreasing | 2026-04-05

## Risk Matrix
Likelihood | High Impact | Medium Impact | Low Impact
High | 9 | 6 | 3
Medium | 6 | 4 | 2
Low | 3 | 2 | 1

## Glossary of Terms
Term | Definition
Risk | The potential for loss or harm.
Likelihood | The probability of the risk occurring.
Impact | The severity of the impact if the risk occurs.
Risk Score | Calculated as Likelihood × Impact.
Response Strategy | The strategy to address the risk (Accept, Avoid, Treat, Transfer).
Residual Risk | The remaining risk after mitigation.
Control Effectiveness | The effectiveness of controls in place to mitigate the risk.
Risk Trend | The direction in which the risk is moving (Increasing, Stable, Decreasing).